## Cover
Scrum Reporting Form
| Day | 2021-04-21
| Due Date | 2021-04-22
| Team Name: | Dream Raptors
| Team Members: | Memhet, Owen, Max
| Project: | Battleship
Division of Labor
| Module Name | Author
You have had an opportunity to decide on a project and start the general set-up for the project. The next step is to go through and identify all the tasks that need to be commpleted to have a finished product for the Final Project Presentation. The Fibonacci Sequence to assign importance of each task. Rate the tasks by the importance of when they need to be done as well as the importance to the completion of the project. Some tasks with a low priority may never be completed. Those can be saved for a later project. Come back to this list each day, mark tasks that have been completed as "Done" and repriotize the remaining tasks.
| Plans for | 2021-04-22
| Team Member | Tasks planned | Prriority
| Owen | Create Github repository and invite members.

## 22 April
Scrum Reporting Form
| Day | 2021-04-22
| Due Day | 2021-04-26
| Team Name: | Dream Raptors
| Team Members: | Mehmet, Owen, Max
| Project: | Battleship
Division of Labor
| Module Name | Author
| Tasks Due | 2021-04-22
| Team Member | Tasks planned | Prriority
| Owen | Battleship github repo | 1
| Plans for | 2021-04-26
| Team Member | Tasks planned
| Owen | Lead how to link repo to Intellij | 1

## 26 April
Scrum Reporting Form
| Day | 2021-04-26
| Due Day | 2021-04-27
| Team Name: | Dream Raptors
| Team Members: | Mehmet, Owen, Max
| Project: | Battlehship
Division of Labor
| Module Name | Author
N/A
| Tasks Due | 2021-04-26
| Team Member | Tasks planned | Priority
| Owen | Lead how to link repo to Intellij | 1
| Plans for | 2021-04-27
| Team Member | Tasks planned
| All | Start working on project

## 27 April
Scrum Reporting Form
| Day | 2021-04-27
| Due Day | 2021-04-28
| Team Name: | Dream Raptors
| Team Members: | Mehmet, Owen, Max
| Project: | Battleship
Division of Labor
| Module Name | Author
Main
| Generate | Owen
Player
| Tasks Due | 2021-04-27
| Team Member | Tasks planned | Prriority
| All | Start working on project | 1
| Plans for | 2021-04-28
| Team Member | Tasks planned
| Mehmet | Have project working. (Commits, pushs, updates)
| Max | Have project working. (Commits, pushs, updates)

## 28 April
Scrum Reporting Form
| Day | 2021-04-28
| Due Day | 2021-04-29
| Team Name: | Dream Raptors
| Team Members: | Mehmet, Owen, Max
| Project: | Battleship
Division of Labor
| Module Name | Author
| GitHub | Owen
| Tasks Due | 2021-04-28
| Team Member | Tasks planned | Prriority
| Max | Have project working. (Commits, pushs, updates) | 1
| Mehmet | Have project working. (Commits, pushs, updates) | 1
| Plans for | 2021-04-29
| Team Member | Tasks planned
| Max | Work on generating game board | 1
| Mehmet | Work on main class (welcome title, maybe rules, etc.) | 2
| Owen | Work on player class

## 29 April
Scrum Reporting Form
| Day | 2021-04-29
| Due Day | 2021-05-03
| Team Name: | Dream Raptors
| Team Members: | Mehmet, Owen, Max
| Project: | Battleship
Division of Labor
| Module Name | Author
| Player/EndGame | Max
| Research/Main | Mehmet
| JavaFx experimentation/ game generate | Owen
| Tasks Due | 2021-04-29
| Team Member | Tasks planned | Priority
| Max | Work on setting up the End of game an experimenting with other means of setting up the computer
| Mehmet | Work on research and the Main class.
| Owen | ABSENT | -
| Plans for | 2021-05-03
| Team Member | Tasks planned

## 3 May
Scrum Reporting Form
| Day | 2021-05-03
| Due Day | 2021-05-04
| Team Name: | Dream Raptors
| Team Members: | Mehmet, Owen, Max
| Project: | Battleship
Division of Labor
| Module Name | Author
| Player/Endgame | Max
| Research/Main | Mehmet
| Absent | Owen
| Tasks Due | 2021-05-03
| Team Member | Tasks planned | Prriority
| Max | Set up the computer branch and begin work on initializing the project | Medium
| Mehmet | Game/board | medium
| Owen | Absent/madeup work | medium
| Plans for | 2021-05-04
| Team Member | Tasks planned

## 4 May
Scrum Reporting Form
| Day | 2021-05-04
| Due Day | 2021-05-05
| Team Name: | Dream Raptors
| Team Members: | Max,Mehmet,Owen
| Project: | Battleship
Division of Labor
| Module Name | Author
| TestFeature/EndGame | Max
| Player | Owen
| Main/generate | Mehmet
| Tasks Due | 2021-05-04
| Team Member | Tasks planned | Prriority
| Max | Continue work on end game and testing features with multiple players | High
| Owen | Player - attack feature | High
| Mehmet | Board setup | High
| Plans for | 2021-05-05
| Team Member | Tasks planned

## 5 May
Scrum Reporting Form
| Day | 2021-05-05
| Due Day | 2021-05-06
| Team Name: | Dream raptors
| Team Members: | max, mehmet, owen
| Project: | Battleship
Division of Labor
| Module Name | Author
| Player/ship setup | Owen
| Scrum form, board | Max
| Board modules | Mehmet
| Tasks Due | 2021-05-05
| Team Member | Tasks planned | Prriority
| Max | Research and understandnew board design features | High
| Mehmet | Research and understandnew board design features | High
| Owen | begin implementing logic to the board nd player sections | Medium
| Plans for | 2021-05-06
| Team Member | Tasks planned

## 6 May
Scrum Reporting Form
| Day | 2021-05-06
| Due Day | 2021-05-10
Team Name:
Team Members:
Project:
Division of Labor
| Module Name | Author
| Tasks Due | 2021-05-06
| Team Member | Tasks planned | Prriority
| Plans for | 2021-05-10
| Team Member | Tasks planned

## 10 May
Final Scrum Reporting Form
| Day | 2021-05-10
| Due Day | 2021-05-11
Team Name:
Team Members:
Project:
Division of Labor
| Module Name | Author
| Tasks Due | 2021-05-10
| Team Member | Tasks planned | Prriority
| Plans for | 2021-05-11
| Team Member | Plans for Presentation